# Lumina Campaign Brief

# Campaign record

Synthetic campaign CAM-2026-Q4. Version 1.0, effective 7 September 2026. Owner: Marketing Lead. Campaign name: Sustainable Workspace.

# Objectives and budget

The target is 120 qualified business enquiries during October 2026. The approved campaign budget is SGD 18000. These are training targets, not actual company results.

# Milestones

Draft creative is due 18 September 2026. Marketing review is due 23 September 2026. Launch is scheduled for 1 October 2026. The performance review is scheduled for 5 November 2026.

# Approved claims

Use the phrase workspace products designed for reuse and repair. Do not claim carbon neutrality, a percentage carbon reduction, or an external certification: none is evidenced in this brief.

# Release checklist

Marketing Lead verifies copy and audience; Finance Lead verifies budget; the Campaign Owner approves release. All email messages and presentation outputs remain drafts until reviewed.