## Slide 1
Launch decision depends on readiness
Planned launch: 1 October 2026
Budget:SGD 18,000; target: 120 qualified enquiries
Review copy, financial evidence, HR training and Operations readiness before approval.
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx

## Slide 2
Historical revenue provides the baseline
Jan–Jun revenue:SGD 933,290
Use the historical pattern as context; it is not an October forecast.
Source:Monthly!A2:B7
Chart: 
| Jan | Feb | Mar | Apr | May | Jun
Revenue SGD | 90150 | 145565 | 130880 | 189070 | 159920 | 217705
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx

## Slide 3
Events leads historical margin contribution
Total margin:SGD 412,193
Margin is revenue minus the supplied cost, not net profit.
Source:Channels!A2:D5
Chart: 
| Web | Partner | Retail | Events
Margin SGD | 84544.39 | 94989.66 | 111411.32 | 121247.22
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx

## Slide 4
Nine employees still need training
47/56 trained: 83.9%
Operations has five of the nine gaps.
Aisha owns completion by 24 September.
Source:HR_Readiness!A2:E6
Chart: 
| HR | Marketing | Finance | Operations
Completion fraction | 0.83333 | 0.875 | 1 | 0.75
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx

## Slide 5
Claims and source limits shape the message
Use:workspace products designed for reuse and repair.
Do not claim carbon neutrality or unsupported certification.
The campaign budget and target are planned; keep them separate from historical performance.
Source:CAM-2026-Q4; HR-01.
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx

## Slide 6
Keep four actions consistent across apps
A01 HR — train remaining staff — 24 September
A02 Marketing — review copy — 23 September
A03 Finance — verify figures — 25 September
A04 Operations — confirm service readiness — 25 September
Record evidence in the Loop register. Human review precedes delivery.
Lumina Living | SW-2026 | Synthetic data | DRAFT FOR REVIEW | Source: Lumina-Business-Data.xlsx