## Scenario
Lab 16: Operate a Governed End-to-End Copilot Pipeline
Lumina Living Pte Ltd · Sustainable Workspace campaign
Topic | 4
Level | Capstone Pipeline
Primary apps | Microsoft 365 Copilot agents + Outlook + Teams + Excel
Goal | Operate the complete intake-to-delivery pipeline with approvals, exception handling, monitoring and staff handover.
Expected output | End-to-end pilot run, approved Outlook draft, Teams handover, monitoring dashboard and staff training plan.
Alignment | K1-K4 · A1-A4
Status | Completed example

## Prompt_Log
Prompt_ID | Purpose | Prompt | Grounding | Reviewer | Status
P16-01 | Operate a Governed End-to-End Copilot Pipeline | Operate the Lumina Living campaign pipeline on the attached pilot cases. Process each case through Intake, Validation, Routing, Analysis, Deck, Approval and Delivery Draft. At every stage record status, owner, timestamp, evidence and exception. Produce an Outlook draft and Teams handover only for approved cases; never send automatically. Summarise throughput, cycle time, exception rate, rework and human overrides, then recommend whether to expand, revise or stop the pilot. | Attached lab files only | Learner | Verified

## Evidence_Register
Evidence_ID | Artifact | Source | Check | Result | Owner | Notes
E01 |  |  | Source and scope verified | PASS | Learner
E02 |  |  | Quantitative claims checked | PASS | Learner
E03 |  |  | Sensitive data reviewed | PASS | Learner
E04 |  |  | Human approval completed | PASS | Learner

## Acceptance_Check
Criterion | Evidence | Status | Reviewer
All pilot cases have a complete audit trail, delivery remains human-controlled and the scale decision is supported by measured operational evidence. | See Evidence_Register | PASS | Learner

## Pilot_Cases
Campaign_ID | Sponsor | Objective | Budget_Band | Launch_Date | Classification | Completeness | Route | Status
LL-001 | Marketing | Workspace launch | Medium | 2026-10-05 | Internal | Complete | Standard Review | Approved for Analysis
LL-002 | Sales | Partner incentive | High | 2026-09-21 | Confidential | Complete | Specialist Review | Human Review
LL-003 | HR | Staff advocacy | Low | 2026-11-03 | Internal | Missing audience |  | Exception
LL-004 | Operations | Service update | Medium | 2026-10-18 | Internal | Complete | Fast-Track Review | Approved for Analysis
LL-005 | Marketing | Duplicate pilot | Medium | 2026-10-05 | Internal | Complete | Standard Review | Duplicate check

## Pipeline_Control
Campaign_ID | Stage | Owner | Status | Timestamp | Evidence | Exception
LL-001 | Intake | Learner | Complete | 2026-08-15 | E-LL-001-1
LL-001 | Validation | Learner | Complete | 2026-08-15 | E-LL-001-2
LL-001 | Routing | Learner | Complete | 2026-08-15 | E-LL-001-3
LL-001 | Analysis | Learner | Complete | 2026-08-15 | E-LL-001-4
LL-001 | Deck | Reviewer | Complete | 2026-08-15 | E-LL-001-5
LL-001 | Approval | Reviewer | Complete | 2026-08-15 | E-LL-001-6
LL-001 | Delivery Draft | Reviewer | Complete | 2026-08-15 | E-LL-001-7
LL-002 | Intake | Learner | Complete | 2026-08-15 | E-LL-002-1
LL-002 | Validation | Learner | Complete | 2026-08-15 | E-LL-002-2
LL-002 | Routing | Learner | Complete | 2026-08-15 | E-LL-002-3
LL-002 | Analysis | Learner | Exception | 2026-08-15 | E-LL-002-4 | Restricted or incomplete
LL-002 | Deck | Reviewer | Exception | 2026-08-15 | E-LL-002-5 | Restricted or incomplete
LL-002 | Approval | Reviewer | Exception | 2026-08-15 | E-LL-002-6 | Restricted or incomplete
LL-002 | Delivery Draft | Reviewer | Exception | 2026-08-15 | E-LL-002-7 | Restricted or incomplete
LL-003 | Intake | Learner | Complete | 2026-08-15 | E-LL-003-1
LL-003 | Validation | Learner | Complete | 2026-08-15 | E-LL-003-2
LL-003 | Routing | Learner | Complete | 2026-08-15 | E-LL-003-3
LL-003 | Analysis | Learner | Exception | 2026-08-15 | E-LL-003-4 | Restricted or incomplete
LL-003 | Deck | Reviewer | Exception | 2026-08-15 | E-LL-003-5 | Restricted or incomplete
LL-003 | Approval | Reviewer | Exception | 2026-08-15 | E-LL-003-6 | Restricted or incomplete
LL-003 | Delivery Draft | Reviewer | Exception | 2026-08-15 | E-LL-003-7 | Restricted or incomplete
LL-004 | Intake | Learner | Complete | 2026-08-15 | E-LL-004-1
LL-004 | Validation | Learner | Complete | 2026-08-15 | E-LL-004-2
LL-004 | Routing | Learner | Complete | 2026-08-15 | E-LL-004-3
LL-004 | Analysis | Learner | Complete | 2026-08-15 | E-LL-004-4
LL-004 | Deck | Reviewer | Complete | 2026-08-15 | E-LL-004-5
LL-004 | Approval | Reviewer | Complete | 2026-08-15 | E-LL-004-6
LL-004 | Delivery Draft | Reviewer | Complete | 2026-08-15 | E-LL-004-7

## Approval_Log
Campaign_ID | Decision | Reviewer | Date | Conditions
LL-001 | Approved | Campaign Director | 2026-08-15 | Draft delivery only; verify recipients

## Pilot_Metrics
Metric | Formula | Result | Target | Status
Throughput | 20 | 20 | 14 | REVIEW
Exception rate | 0.28571 | 0.28571 | 0.2 | REVIEW
Human overrides | 0 | 0 | 1 | PASS