## Slide 1
Lumina HR service portfolio - 30 September
Closed 48 + Cancelled 12 + Backlog 60 = 120. Recorded cost S$35,827.50; this is not a budget or saving.
Observation -> evidence -> proposed action -> decision
TGS-2024043856 v9.1 | Synthetic Lumina example | 2026-09-30 | All filters All | Slide1
Notes: Counts partition the selected source table exactly; recorded cost includes all statuses. Do not infer a budget or savings.

## Slide 2
50 of 60 backlog cases are overdue
On-time closure rate = 30/48 = 62.5%. Overdue backlog: 50, using Due_Date < 30 September 2026. Closed-only denominator, not all 120 cases.
Chart: 
| Retail Sales | Operations | Finance | Technology | Marketing
Backlog HR cases by department | 8 | 12 | 16 | 20 | 4
TGS-2024043856 v9.1 | Synthetic Lumina example | 2026-09-30 | All filters All | Slide2
Notes: Closed on/before Due_Date is on time. Numerator 30 and denominator 48 are both source-derived. A different scope must be recalculated.

## Slide 3
6 backlog cases need an assignment proposal
Unassigned backlog: 6. Compare primary category and available hours across 8 synthetic HR officers. Current owners remain unchanged; specific suitable/approved allocations UNKNOWN.
Validate constraints before confirming an operational change.
TGS-2024043856 v9.1 | Synthetic Lumina example | 2026-09-30 | All filters All | Slide3
Notes: Six blank current owners are in backlog. HR_Officers table contains planning inputs, not approval or comprehensive policy/capacity evidence.

## Slide 4
Decision requested: review the proposed priorities
Requested decision: review and approve or revise the proposed recovery priorities and assignment checks. Decision owner, approval outcome and next review date UNKNOWN until supplied. No email sent and no source assignment changed.
Static presentation: verified snapshot, not an automatic live link.
TGS-2024043856 v9.1 | Synthetic Lumina example | 2026-09-30 | All filters All | Slide4
Notes: Ask for a decision without claiming one was made. The PowerPoint is a static snapshot; retain the interactive workbook and evidence register.